## Start Here
CSV Import Production-Readiness Plan
Use this workbook with the generated fixtures and round-trip comparator. A green upload message is not sufficient evidence of a successful import.
Known failure | Users can correct validation errors, but corrected or surrounding field values may not survive validation, submission, persistence, or search display.
Immediate safety rule | Keep bulk production import behind a feature flag. Use only synthetic or isolated canary data until every mandatory go-live gate passes with evidence.
Primary diagnostic | Trace one row across: raw CSV -> parsed row -> mapped draft -> corrected draft -> commit payload -> backend DTO -> database -> search/read response.
Non-negotiable invariant | After correcting one invalid cell, every untouched cell must remain identical. The committed and re-read record must match the latest corrected draft.
Execution order
1. Replace sample_golden.csv with a small known-good, production-shaped synthetic file.
2. Generate the valid control plus 20 single-defect fixtures using generate_import_test_cases.py.
3. Run the valid control first. Stop immediately if it does not round-trip with zero differences.
4. Run each error case, correct only the intended defect, and verify all untouched fields remain unchanged.
5. Inspect the commit request and compare the corrected expected CSV against the exported/search result.
6. Complete the go-live gates, canary, reconciliation, and rollback rehearsal before importing the waiting backlog.
Evidence required for every run
- Fixture name and SHA-256 |  | - Environment and application build/commit
- Import ID/correlation ID |  | - Preflight error and source row number
- Before/after correction values |  | - Commit request payload with sensitive data redacted
- Inserted/updated/failed counts |  | - Database or export/search result
- Round-trip diff and summary |  | - Screenshot or recording

## 20 Error Cases
20 Controlled CSV Import Cases
Each fixture contains one intentional defect. For correctable cases, fix only the flagged value and prove all untouched fields survive every stage.
Case ID | Fixture | Single Defect | Owning Layer | Expected Preflight / Security Behavior | Correction | Retention Assertion | Commit / Persistence Assertion | Priority | Result | Build / Commit | Import ID | Evidence Link | Notes
IMP-01 | 01_missing_required_header.csv | Required header 'full_name' is missing. | Schema mapping | Preflight must block the file and identify the missing canonical field. | Restore the exact required header or map the source header explicitly. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P0 | Not Run
IMP-02 | 02_unexpected_extra_header.csv | One unsupported extra header is present. | Schema mapping | Preflight must reject or require an explicit mapping; it must not silently discard the column. | Remove the column or map it to a supported destination field. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P0 | Not Run
IMP-03 | 03_duplicate_header.csv | Header 'full_name' appears twice. | CSV parser/schema | Preflight must block the file and report the duplicated header name. | Remove or rename the duplicate header. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P0 | Not Run
IMP-04 | 04_header_case_mismatch.csv | Required header case changed from 'full_name' to 'FULL_NAME'. | Schema mapping | Behavior must be deterministic: either normalize case and show the mapping, or block with an exact header error. | Map 'FULL_NAME' to 'full_name' or restore canonical casing. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P1 | Not Run
IMP-05 | 05_header_trailing_space.csv | Required header 'full_name' has one trailing space. | Schema normalization | The importer must trim headers before mapping or show a clear mapping error; it must not create an empty field silently. | Trim the header or confirm the normalized mapping. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P0 | Not Run
IMP-06 | 06_blank_required_value.csv | One row has a blank required value in 'full_name'. | Row validation | Preflight must identify the exact row and field and keep every other cell visible and editable. | Enter a valid value in the flagged cell. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P0 | Not Run
IMP-07 | 07_whitespace_only_required_value.csv | One required value in 'full_name' contains spaces only. | Normalization/validation | The importer must trim before validation and flag the value as blank. | Enter a non-whitespace value. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P0 | Not Run
IMP-08 | 08_duplicate_id_within_file.csv | Two rows share the same 'record_id' value. | Uniqueness validation | Preflight must flag both conflicting row numbers and must not commit either row silently. | Change one ID or select an explicit update/upsert policy. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P0 | Not Run
IMP-09 | 09_invalid_email.csv | One value in 'email' is not a valid email. | Type/format validation | Preflight must flag only the invalid cell and preserve the rest of the row. | Replace it with a valid email or blank it only if the field is optional. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P1 | Not Run
IMP-10 | 10_invalid_date.csv | One value in 'start_date' is an impossible date. | Type/format validation | Preflight must reject the impossible date and display the accepted date format. | Enter a valid calendar date in the documented format. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P1 | Not Run
IMP-11 | 11_invalid_numeric.csv | One value in 'amount' contains a letter in a numeric field. | Type/format validation | Preflight must flag the exact cell and must not coerce it to zero or null. | Replace the value with a valid number. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P1 | Not Run
IMP-12 | 12_invalid_enum.csv | One value in 'status' is outside the allowed set. | Business validation | Preflight must show the allowed values and keep the original value available for correction. | Select or enter one allowed value. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P1 | Not Run
IMP-13 | 13_over_max_length.csv | One value in 'notes' is 81 characters long. | Length validation | Preflight must show the configured maximum and must never truncate silently. | Shorten the value to 80 characters or fewer. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P1 | Not Run
IMP-14 | 14_too_many_columns_in_one_row.csv | One data row has one extra unquoted column. | CSV parser | Parsing must stop or quarantine the malformed row and report expected versus actual column count. | Remove the extra delimiter/cell from the row. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P0 | Not Run
IMP-15 | 15_too_few_columns_in_one_row.csv | One data row has one fewer column than the header. | CSV parser | Parsing must flag the malformed row; missing tail cells must not shift data into the wrong fields. | Add the missing delimiter/value in the correct position. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P0 | Not Run
IMP-16 | 16_unbalanced_quote.csv | One row contains an opening quote without a closing quote. | CSV parser | The importer must report a malformed quoted field and must not merge subsequent rows into it. | Close or remove the unmatched quote. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P0 | Not Run
IMP-17 | 17_wrong_delimiter.csv | The file uses ';' instead of the configured ',' delimiter. | CSV parser/configuration | The importer must detect the likely delimiter or block with a clear delimiter message; it must not treat the entire row as one field. | Choose the detected delimiter or regenerate the file with the configured delimiter. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P0 | Not Run
IMP-18 | 18_non_utf8_encoding.csv | The file is Windows-1252 encoded rather than UTF-8. | File decoding | The importer must reject with a clear encoding message or require an explicit encoding selection; it must not replace characters silently. | Save as UTF-8 or explicitly select Windows-1252 if supported. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P1 | Not Run
IMP-19 | 19_null_byte_in_field.csv | One value in 'full_name' contains a null byte. | Input sanitization | The importer must reject the exact row/field and must not truncate the value at the null byte. | Remove the null byte and revalidate. | After correction, every untouched cell must remain byte-for-byte equivalent to the parsed draft value. | The commit payload and persisted record must contain the corrected row plus all untouched field values. | P0 | Not Run
IMP-20 | 20_formula_injection.csv | One value in 'notes' begins with a spreadsheet formula marker. | Security/sanitization | The application must treat it as data. Any CSV/XLSX error export must escape formula-leading characters. | Confirm the value is intended, then store/display it as inert text or reject it under the security policy. | The literal value must remain inert text; no correction or export may execute it as a formula. | Persisted and exported values must be safely escaped or rejected according to policy, with no silent modification. | P0 | Not Run

## Fix Plan
Production Fix and Rollout Plan
Prove the failing boundary first, then fix and automate. Avoid declaring success based on UI behavior alone.
Phase | Objective | Key Actions | Primary Owner | Required Evidence | Exit Criteria | Status | Notes
0 - Contain | Prevent additional data loss | Feature-flag bulk import; allow only isolated synthetic/canary files; preserve failed job evidence. | Product + Engineering | Feature flag state; incident record; backlog inventory | No unverified production bulk imports can run. | Not Started
1 - Instrument | Locate the exact loss boundary | Add import ID, row ID, draft revision, schema version, row/field counts, payload counts, persistence counts, and read-after-write status. | Backend + Frontend | One trace spanning raw file to search response | The first stage where a value changes or disappears is proven. | Not Started
2 - Reproduce | Create a deterministic failing test | Run valid control and targeted blank/format fixture; capture draft state and network payload before and after correction. | QA + Engineering | Fixture hash, recording, payload, DB/export comparison | Failure reproduces consistently or instrumentation proves another environment issue. | Not Started
3 - Correct | Fix the owning layer | Implement canonical draft state, pure validation, controlled inputs, stable row keys, current-state serialization, backend mapping, atomic write, or search projection fix. | Owning Engineer | Code review; unit/component/integration tests | The deterministic regression test passes locally and in CI. | Not Started
4 - Harden | Cover the whole import contract | Add 20 fixtures, idempotency, duplicate policy, rollback, encoding, security, large-file, timeout, and concurrent-import tests. | QA Automation + Backend | CI run with artifacts and zero round-trip differences | All mandatory automated and manual cases pass. | Not Started
5 - Canary | Verify production-shaped behavior safely | Import a small synthetic or isolated tenant batch; reconcile source, payload, DB, export, and search; rehearse rollback. | Release Owner | Canary import ID; reconciliation report; rollback evidence | Zero mismatches and monitoring remains healthy. | Not Started
6 - Backlog | Import waiting data with controls | Process in bounded batches; hash files; record import IDs; stop automatically on any mismatch; retain reconciliation outputs. | Operations + Data Owner | Per-batch source/actual comparison and approval | All batches verified; no unresolved field-loss alerts. | Not Started
7 - General Availability | Remove temporary controls | Review metrics over multiple verified batches; document limits, support runbook, and ownership; remove feature flag only after sign-off. | Product + Engineering | Go-live gate approvals; operational runbook | All gates Pass and owners approve production use. | Not Started

## Root Cause Trace
Root-Cause Trace
Follow one row in sequence. Stop at the first checkpoint where a value differs from the previous stage.
Checkpoint | Question | Evidence to Capture | If Values Are Correct | If Values Are Missing / Changed | Likely Fix | Owner | Result | Evidence Link
1. Raw file | Are the expected headers and raw cell bytes present? | File hash; encoding; delimiter; source row | Continue to parser. | Source file/export problem. | Correct source generation; document encoding/delimiter contract. |  | Not Run
2. Parsed row | Did the parser produce the correct number of cells and exact strings? | Parsed row JSON; source row number | Continue to mapping. | Parser/delimiter/quote/encoding defect. | Use strict parser settings and actionable malformed-row errors. |  | Not Run
3. Canonical mapping | Are source headers mapped to the intended canonical field keys? | Header map and schema version | Continue to draft. | Header normalization or mapping defect. | Versioned schema map; reject unknown or duplicate fields. |  | Not Run
4. Editable draft | Does the initial form state contain every mapped value? | Draft snapshot with row ID/revision | Continue to correction. | Draft initialization or table virtualization defect. | Initialize once; stable row IDs; canonical parent-level store. |  | Not Run
5. After correction | After changing one cell, do all other values remain identical? | Before/after draft snapshots | Continue to revalidation. | State mutation, uncontrolled input, index key, or local-only cell state. | Controlled inputs; immutable nested updates; stable keys. |  | Not Run
6. After revalidation/navigation | Do values survive validation, sort, pagination, and wizard navigation? | Draft revision and snapshots after each action | Continue to request. | Validation/effect resets draft or unmounted fields are lost. | Separate error map; remove reset effects; persist canonical draft. |  | Not Run
7. Commit request | Does the network payload contain the latest correction and all fields? | Redacted request body; draft revision | Continue to API DTO. | Submit uses stale parsed state or stale closure. | Serialize latest draft; flush debounced edits before submit. |  | Not Run
8. Backend DTO | Does API validation retain all canonical fields? | Validated DTO and field counts | Continue to persistence. | DTO/allowlist/coercion strips values. | Align schema; reject unknowns; never silently coerce invalid data to null. |  | Not Run
9. Database write | Do returned/persisted values match the validated DTO? | Transaction result; RETURNING values; row/field counts | Continue to read path. | ORM field list, upsert clause, trigger, or rollback defect. | Atomic write; complete field mapping; verify counts before success. |  | Not Run
10. Search/read response | Does the user-facing API/search result match the database? | Read response; index job state; cache state | Root cause resolved; automate regression. | Serializer, index mapping, stale cache, or display property mismatch. | Fix projection/indexing; expose truthful pending/failed state. |  | Not Run

## Schema Mapping
Import Schema and Field Mapping
Complete this before production testing. Unknown, duplicate, or silently discarded fields must be treated as explicit errors or reviewed mappings.
Source Header | Canonical Field Key | Display Label | Data Type | Required | Max Length | Accepted Format | Allowed Values | Trim | Empty Policy | Database Column | API Field | Search / Display Field | Owner | Status | Notes

## Telemetry
Import Observability Contract
Log identifiers, counts, hashes, and state transitions. Do not log raw sensitive field values.
Stage | Field / Metric | Type | Required | PII Policy | Purpose | Alert / Invariant | Implemented | Evidence
File | import_id / correlation_id | String | Yes | Non-PII | Join all stages and support incident investigation. | Present at every stage. | No
File | tenant_or_account_id | String | Yes | Internal identifier | Scope jobs and duplicate policy. | Must match authenticated context. | No
File | file_sha256 | String | Yes | Non-PII hash | Idempotency and evidence. | Same hash from upload through commit. | No
File | file_size_bytes | Integer | Yes | Non-PII | Limits and capacity monitoring. | Reject over documented maximum. | No
Parse | encoding / delimiter | String | Yes | Non-PII | Diagnose parsing discrepancies. | Detected or explicitly selected. | No
Schema | schema_version / header_map_version | String | Yes | Non-PII | Prevent stale mappings. | Preflight and commit versions must match. | No
Parse | parsed_row_count | Integer | Yes | Non-PII | Baseline row count. | Must equal expected source rows. | No
Validate | invalid_row_count / invalid_field_count | Integer | Yes | Non-PII | Quality and error reporting. | Commit blocked unless policy allows and user explicitly opts in. | No
Draft | draft_revision / correction_count | Integer | Yes | Non-PII | Detect stale submissions. | Commit revision must equal latest draft revision. | No
Commit | payload_row_count / mapped_field_count | Integer | Yes | Non-PII | Detect dropped rows or fields before persistence. | Must match validated draft. | No
Persistence | inserted / updated / skipped / failed | Integer | Yes | Non-PII | Truthful job result. | Accepted must reconcile to outcomes. | No
Persistence | expected_non_null_fields / actual_non_null_fields | Integer | Yes | Non-PII | Detect blank-field data loss. | Mismatch forces rollback or verification_failed. | No
Persistence | transaction_outcome | Enum | Yes | Non-PII | Confirm atomicity. | No completed state after rollback. | No
Verification | read_after_write_status | Enum | Yes | Non-PII | Confirm saved values are readable. | Completed only when verified. | No
Search | indexing_status / index_lag_ms | Enum/Integer | When applicable | Non-PII | Explain delayed visibility. | Alert on failed or excessive lag. | No
Timing | duration_ms_by_stage | Integer | Yes | Non-PII | Performance baselines and timeouts. | Alert over agreed thresholds. | No

## Go-Live Gates
Mandatory Go-Live Gates
Every gate must be Pass with reviewable evidence before bulk production data is imported.
Gate | Category | Mandatory Pass Criterion | Evidence Required | Owner | Result | Evidence Link | Notes
G01 | Control | Valid control imports and the round-trip comparator reports zero differences. | Fixture hash; import ID; diff and summary |  | Not Run
G02 | Negative tests | All 20 controlled fixtures produce the expected validation, parser, or security behavior. | Completed 20 Error Cases sheet |  | Not Run
G03 | Field retention | Every correctable case retains all untouched values through revalidation, sorting, pagination, and wizard navigation. | Before/after draft snapshots and recordings |  | Not Run
G04 | Payload | Commit request exactly matches the latest corrected draft revision. | Redacted request and draft snapshot |  | Not Run
G05 | Persistence | Accepted, persisted, and verified row counts match; mapped field counts do not fall. | API logs, transaction result, verification report |  | Not Run
G06 | Read path | Database, export, API, and search/display values are reconciled. | Round-trip comparison through user-facing read path |  | Not Run
G07 | Idempotency | Retrying the same commit cannot create duplicates or inconsistent results. | Repeated-request test and job record |  | Not Run
G08 | Duplicate policy | Within-file and existing-record duplicates follow an explicit tested policy. | Reject/update/upsert tests |  | Not Run
G09 | Rollback | A forced mid-batch failure rolls back or quarantines exactly according to policy. | Failure injection and database reconciliation |  | Not Run
G10 | Security | Formula-leading values and malformed content remain inert; exports are safely escaped. | Security case results and exported file review |  | Not Run
G11 | Performance | 1k, 10k, and expected maximum volume pass documented time and memory limits. | Load-test report and limits |  | Not Run
G12 | Observability | Dashboard, logs, job states, and alerts expose every required invariant without raw PII. | Telemetry review and alert test |  | Not Run
G13 | Canary | A production-shaped isolated canary has zero mismatches and a rehearsed rollback. | Canary reconciliation and rollback evidence |  | Not Run
G14 | Approval | Product, engineering, QA, and data owner approve based on evidence. | Named sign-offs |  | Not Run

## Run Log
Import Test Run Log
Record one row per execution. Attach network, persistence, comparison, and visual evidence.
Run ID | Date / Time | Environment | Build / Commit | Fixture | File SHA-256 | Import ID | Tester | Preflight Result | Commit Result | Expected Rows | Persisted Rows | Field Mismatches | Search Verified | Overall Result | Evidence Folder / Link | Notes

## Field Retention Check
Field-Level Retention Evidence
Use one section per affected row. Untouched fields must remain identical from parsed value through search/export.
Source Row | Stable Row ID | Field | Source / Parsed Value | Initial Draft | After Correction | After Revalidation | Commit Payload | Database | Search / Export | Result | Notes